Project Charter Document

Project Name:	System Replacement Project - “Project New Horizon”

Department:	Operations

Focus Area:	Companywide

Product/Process:	Existing and New Policy Administration Systems and Interfaces

Prepared By

| Document Owner(s) | Project/Organization Role |
| --- | --- |

Project Charter Version Control

| Version | Date | Author | Change Description |
| --- | --- | --- | --- |
| 1.0 |  |  | Document created |
|  |  | [Replace this text with the name of the Change Owner.] | [Replace this text with a list of changes for this Owner on this Date and Version.] - [Change 1] - [Change 2] - [Change n] |

TABLE OF CONTENTS

1	PROJECT CHARTER PURPOSE	3

2	PROJECT EXECUTIVE SUMMARY	3

3	PROJECT OVERVIEW	3

4	PROJECT SCOPE	3

4.1	Goals and Objectives	3

4.2	Organizational Impacts	3

4.3	Patient/Customer Impacts	4

4.4	Project Deliverables	4

4.5	Exceptions to Brand Standards	4

4.6	Deliverables Out of Scope	4

4.7	High Level Project Timeline	5

4.8	Estimated Project Costs	5

5	PROJECT CONDITIONS	5

5.1	Project Assumptions	5

5.2	Critical Success Factors	6

5.3	Project Issues	6

5.4	Project Risks	6

5.5	Project Constraints	6

6	Project Structure Approach	6

7	Project Team Organization Plans	7

8	PROJECT REFERENCES	9

9	APPROVALS	9

10	APPENDICES	10

10.1	Document Guidelines	10

10.2	Project Charter Document Sections Omitted	10

# PROJECT CHARTER PURPOSE

The project charter defines the scope, objectives, and overall approach for the work to be completed. It is a critical element for initiating, planning, executing, controlling, and assessing the project. It should be the single point of reference on the project for project goals and objectives, scope, organization, estimates, work plan, and budget. In addition, it serves as a contract between the Project Team and the Project Sponsors, stating what will be delivered according to the budget, time constraints, risks, resources, and standards agreed upon for the project.

# PROJECT EXECUTIVE SUMMARY

[Replace this text with a high-level description of the goals, objectives, and approach for the project.] Summary derived after completing rest of charter

# PROJECT OVERVIEW

Current PAS is nearing end of life – increasingly difficult and costly to update and/or modify.  Architecture limits integrations with other systems and does not support newer digital technology.  Significant risks to ongoing business operations and staying current with consumer service and product expectations.  Legacy technology has been identified as leading contributor to declining revenue and membership as LifeCo Inc has not been able to stay current with marketplace.  In addition to cost-effective changes to products and services offered, improved customer experience and operational efficiencies should be achieved.  See also PM03, Project Deliverables

# PROJECT SCOPE

## Goals and Objectives

| Goals | Objectives |
| --- | --- |
| Full completion within 2 years | - Legacy system decommissioned, within 6 months post conv. - Minimal service disruption at go-live: 98% time and accuracy standards met within 2 weeks of go-live. - Within budget |
| Process integrity on actively sold products | - Eliminate all manual interventions/workarounds on actively sold products to produce statements and values |
| Online customer services tools | - Addition of secure, online tools to provide policy information and values, and provide self-service functionality - Promote online services so that 1 year post go-live, 30% of CS inquiries handled online |

## Organizational Impacts

| Organization | Impact to and Participation of Organization |
| --- | --- |

## Patient/Customer Impacts

| Patient/Customer | Impact to and Participation of Patients/Customers |
| --- | --- |

## Project Deliverables

| ID | Deliverable | Responsible |
| --- | --- | --- |
| PM01 | Project Charter | Jane, Program Mgr. |
| PM02 | Project Plan | Jane, Program Mgr. |
| PM03 | Project Business Case | Joe, Operations VP |
| PM04 | Project Budget | Jane, Program Mgr. |
| PM05 | Project Resource Request | Jane, Program Mgr. |
| PM06 | Communication Plan | Judy, Marketing |
| PM07 | Risk Assessment | Jim, CRO |
| PM08 | Implementation Plan | Jane, Program Mgr. |
| PM09 | Project Assessment | Jim, CRO |
| TST01 | Testing Plan | Jolene, BA |
| TRN01 | Training Plan | Jerry, Trainer |
| <project specific> |  |  |

## Exceptions to Brand Standards

[Relative to the scope and deliverables of the project, identify all exceptions to existing brand standards established for processes and technology platforms]

- Technology

- Process

## Deliverables Out of Scope

- Collateral system modifications due to new data structures, except for upfront UW/Application system

- Modifications/Tasks to address future products other than IUL

- Back-end reporting and data warehouse

## High Level Project Timeline

| Project Milestone | Delivery Date | Deliverable(s) Included |
| --- | --- | --- |
| Project Kickoff | 04/15/25 | Project Team, Project Schedule, Project Scope, Internal Communication Plan |
| Phase 1- New Business set-up | 10/15/25 | All active new business policies set-up and tested, staff training completed, claims and policy services functional testing, integration testing |
| Phase 1 – Go/No Go | 10/15/25 | Stakeholder decision to go-live |
| Phase 1 – Go live | 12/1/25 | Go-live new business |
| 2 systems year-end reporting | 1/31/26 | Reports from both PAS systems for annual statement and regulatory filings |
| Phase 2 – In force conversion | 9/15/26 | All active policies set-up and tested, staff training completed, claims and policy services functional testing, integration testing |
| Phase 2 – Go/No Go | 9/15/25 | Stakeholder decision to go-live |
| Phase 2 – Go live | 11/1/25 | Go-live new business |
| Decommissioned legacy systems | 4/1/26 | Systems and data archived, no further support |

## Estimated Project Costs – 4 years

| Category | Description | Cost |
| --- | --- | --- |
| Software | Applications purchased – testing, data mapping, cybersecurity | $ 110,000 |
| Hardware | New hardware necessary for new PAS | $ 55,000 |
| Services | Internal staff and contracted professional services for project | $ 1,750,000 |
|  | Total Capital Investment | $1,915,000.00 |
| Software Maintenance |  | $ |
| Hardware Maintenance | Infrastructure upgrades $20,000 per year | $ 80,000 |
| Subscription/Service Fees | $125,000 x 4 years plus per $1.20 per month per subscriber over 50,000; BI tools @ $5,000 per year licenses | $ 592,000 |
| Training | Contracted services and materials | $ 100,000 |
| Travel | To vendor HQ, remote staff in person periodically, OT dinners | $ 75,000 |
|  | Total Operational Expense | $847,000.00 |
|  | Total Estimated Cost | $2,762,000.00 |

# PROJECT CONDITIONS

## Project Assumptions

- Dedicated staff during term of project will be identified and will remain consistent throughout the project life

- Implement out-of-the box functionality, unless modification approved by Executive Team/Steering Committee

- Governance with routine project updates and project variances reviewed by Executive Team/Steering Committee

- No large enterprise projects will be initiated during the project

- The vendor will manage all infrastructure and services (SAAS model)

## Critical Success Factors

- Executive sponsorship

- On time new business Go Live, with full online services.

- Minimal variance to service standards at Go Live

- Overall improved operational efficiencies realized within 1 month of Go Live

- Business growth of XX% in the next 12 months

## Project Issues

Priority Criteria

1 − High-priority/critical-path issue; requires immediate follow-up and resolution.

2	 − Medium-priority issue; requires follow-up before completion of next project milestone.

3	 − Low-priority issue; to be resolved prior to project completion.

4 − Closed issue.

| # | Date | Priority | Owner | Description | Status & Resolution |
| --- | --- | --- | --- | --- | --- |
| 1 | [mm/dd/yy] |  |  | [Issue 1 description] | [Replace this text with Status and Proposed or Actual Resolution.] |
| 2 | [mm/dd/yy] |  |  | [Issue 2 description] | [Replace this text with Status and Proposed or Actual Resolution.] |

## Project Risks

| # | Risk Area | Likelihood | Risk Owner | Project Impact-Mitigation Plan |
| --- | --- | --- | --- | --- |
| 1 | [Project Risk] | [High/Medium/Low] |  | [Replace this text with a description of the Mitigation Plan.] |
| 2 | [Project Risk] | [High/Medium/Low] |  | [Replace this text with a description of the Mitigation Plan.] |

## Project Constraints

- [Replace this text with a description of a Constraint.]

- [Constraint 2]

- [Constraint 3]

# Project Structure Approach

This project will be staffed and organized to ensure necessary resources are available to achieve intended outcomes. The structure enables accountability, transparency and responsive decision-making.

Section 7 defines the roles and responsibilities within the project.  Empowerment and scope of project management and staff is defined within the roles and responsibilities.

Once the project plan, timeline and budget have been established (collectively ‘the Project’), staff will work to achieve the Project goals.

The Steering Committee will meet regularly to review status and assess variances.  If negative variances to the Project cannot be overcome, then project plan change recommendations will be developed and escalated for approval.  Changes may include reductions and/or increases to scope, budget, and timeframe.

| # | Tollgate / Stage Gate | Date | Milestones¦Deliverables | Required to Proceed |
| --- | --- | --- | --- | --- |
| 1 | Design Stage |  | Stakeholder consensus for readiness/sign-off | Yes |
| 2 | Data conversion |  | 99% of data converted via programming | Yes |
| 3 | Testing Stage |  | Stakeholder consensus for readiness/sign-off | Yes |
| 4 | Training Stage |  | Stakeholder consensus for readiness | Yes |
| 5 | Go/No Go Decisions |  | Stakeholder consensus for readiness | Yes |

# Project Team Organization Plans

| Project Team Role | Project Team Member(s) | Responsibilities |
| --- | --- | --- |
| Executive Management | CEO, E/S/VP Operations | - Assure execution of the project is consistent with mission, vision, values, and strategic objectives of the organization - Provide the project budget - Review and final approval of project change orders escalated by the Project Steering Committee |
| Project Steering Committee | [Consider who are the primary stakeholders – for admin systems consider CMO, COO, CIO, CRO/Audit, CFO/Controller, and Actuarial] | - Provide line of business expertise and oversight to the project - Control project scope, budget and schedule through formal review and approval of project change orders - Review and approve the resolution of project-level issues |
| Project Sponsor/Steering Committee Chair | [Names] | - Maintains project alignment with strategic plan - Project level decision making relative to requirements and design - Scope Management - Escalates project issues to Steering Committee and Executive Management - Ensure line of business resources are available to the project - Project Evangelist |
| Project Managers | [Names] | - Schedule Management - Budget Management - Vendor Management - Resource Management - Project Communication - Project Reporting - Identify and escalate project-level issues for Project Sponsor and Steering Committee review - Risk assessment and mitigation - Preparation of change orders documenting impacts to schedule, budget, and scope |
| Technical Lead | [Names] | - Provides subject matter leadership and coordination - Identifies and resolves issues - Subject matter decision making - Leads requirements and design activities related to technical aspects of the solution |
| Functional Lead | [Names] | - Provides subject matter leadership and coordination - Identifies and resolves issues - Subject matter decision making - Leads requirements and design activities related to functionality of the solution |
| Team Members | [Names] | - Provide subject matter expertise - Contribute to the development of requirements - Contribute to design of the solution - Participate in the testing of the solution - Support training and implementation activities |

# PROJECT REFERENCES

| Milestone | Deliverable |
| --- | --- |
| [Name of Document/Reference] | [Description with available hyperlinks] |

# APPROVALS

Prepared by

Project Manager

Approved by	__________________________________

Project Sponsor

__________________________________

Executive Sponsor

__________________________________

Client Sponsor

# APPENDICES

## Document Guidelines

## Project Charter Document Sections Omitted