## Project Plan
Industry Advantage Implementation Plan Template
Task | Participant | Expected effort | Complete by (from subsciption activation date) | LOMA Reference Materials | Notes
Industry Advantage Awareness and Communications Planning
Build awareness with business unit leaders | Industry Advantage Liaison | 1 hour | T-10* | Email Template for Sr. Leaders | *10 days ahead of subscription activation
Solicit participation from business unit leaders | IA Liaison / Business Heads | 1 hour | T-10
Identify target participating teams within business units | IA Liaison | 1 hour | T-8 |  | Desired groups of learners within business units
Email managers of target teams, if applicable | IA Liaison | 1 hour | T-7 | Email Template for Managers | Request participation of desired teams
Share subscription expectations/benefits/timelines with managers | IA Liaison / Managers | 1 hour | T-7
Secure particiation of target teams | IA Liaison / Managers | 30 min | T-5
Alternatively, if pursuing First Come/First Served implementation
Email staff for participation in Industry Advantage | IA Liaison | 1 hour | T-8 | Email Template for Learners
Establish Roll Out Goals
Determine Subscription Learner Criteria | IA Liaison / L&D | 30 min | T-7
Determine Subscription Goals for org and how to measure | IA Liaison / Managers | 1 hour | T-7 | Member KPIs tab of this workbook | Surveys, emails, 1:1's, stakeholder group debriefs
Identify required or recommended IA content for each team, if applicable | IA Liaison / Managers | 3 hours | T-3 | Recommended Courses by Operational Area
Subscription Set Up
Fill out Account Set Up form | Industry Advantage Liaison/LMS Admin | 10 min | T-10 | LOMA Account Setup Form
Schedule Kick-off with LOMA | LOMA IA Admin / IA Liaison | 30 min | T-9
Attend Kick-off meeting | LMS Admin /IA Liaison | 30 min | T-5
Test Content Controller URL | LMS Admin /IA Liaison |  | T-4 |  | Whitelist this URL if blocked: https://llglobal.contentcontroller.com
Determine if org will set up Learning Paths | LOMA IA Admin / IA Liaison / manager
Create communication plan for learners | IA Liaison | 1 hour | T-7 | Email Template for Learners
Request names of Learners from managers, if applicable | IA Liaison | 30 min | T-4
Set up IA course usage contest (if desired) | IA Liaison | 2 hours | T-3 |  | Encourage participation by encouraging business units to compete against each other (ex: number of courses completed per person) - centralize leaderboard, let teams come up with own names, offer prizes, etc.
Rollout
Receive starter pack of 5 proxy files from LOMA and load into LMS | LMS Admin | 5 min | T-5 |  | Organize all IA content in single location in LMS, if possible
Test LMS functionality with test files |  | 2 hours | T-4
Upon successful testing, notify LOMA and receive remaining proxy files to load |  | varies | T-3
Create Learning Paths in LMS (if desired) | LMS Admin | 2 hours | T-2 | Industry Advantage Learning Paths
Load course metadata into LMS | LMS Admin | varies | T-2 |  | Implementation time will vary by LMS and amount of metadata used
Set up IA access in LMS for designated learners | LMS Admin | 1 hour | T-1
Notify participants, managers and business leaders that courses are live | IA Liaison / Managers | 30 min | Go Live | Email templates for Learners | Provide instructions for access, encourage usage, communicate contest (if applicable)
Subscription Management
Begin Monitoring IA usage | LMS Admin /IA Liaison | 30 min | T+14 |  | Run initial usage report from LMS
Begin usage encouragement communications with learners and managers | IA Liaison / Managers | 1 hour | T+7 | Learner Highlights, IA stats, Intranet recognition, contest (if applicable) | Contest leaderboard update (if applicable)
Create and run regular usage reports | LMS Admin /IA Liaison | 1 hour | T +14 |  | Share team-specific results with managers and business leaders
Regular check-ins with LOMA | IA Liaison / LMS Admin | 1 hour | Bi-monthly |  | LOMA will offer and schedule regular check-in meetings; issues should be reported to LOMA immediately
Regularly measure results against established KPIs | IA Liaison / Managers | 2 hours | varies | Member KPIs tab in this workbook | Suggested KPIs, goals, and measurement tools are listed on the Member KPIs tab of this workbook; adapt as appropriate for company's goals

## Seat Distribution
Sample Seat Allocation Worksheet (assumes 150-seat subscription)
Business Unit | Seats | Learning Path Recommendations* | Course Recommendations
Operations | 50 | This section to be competed one week prior to subscription activation date.
Human Resopurces / L&D | 25
Finance | 10
Investment Management | 5
Enterprise Risk Management | 5
Information Technology | 20
Marketing | 20
Distribution | 15
* Employees new to industry or line of business should complete Fundamentals Learning Path (Life, Annuity, or Workplace Benefits)

## Member KPIs
KPI / IA Goal | Measurement tool | Suggested Goal | Result | Observations
Onboarding and Support
Time to fully populate the LMS | Participant reporting | 7 days
Time to allocate 50% of seats | Participant reporting | 10 days
Time to allocate 100% of seats | Participant reporting | 21 days
Amount of technical issues | Participant reporting | within acceptable tolerance (<5)
Content
Overall quality | LOMA survey | at least 80% positive
Positive impact on career development | LOMA survey | at least 80% positive
Format | LOMA survey | at least 80% positive
Length | LOMA survey | at least 80% positive
Breadth of topics | LOMA survey | at least 80% positive
Learning paths | LOMA survey | at least 80% positive
Alignment of content with business acumen curriculum | Participant reporting
Usage
Percentage of seat holders accessing content @ 30 days | Internal LMS reporting | >40%
Percentage of seat holders accessing content @ 45 days | Internal LMS reporting | >80%
Course views by Learner @75 days | Content Controller data from LOMA | 3+
Percentage of IA course library accessed @ 30 days | Content Controller data from LOMA | >20%
Percentage of IA course library accessed @ 45 days | Content Controller data from LOMA | >40%
Benchmarking
Percentage of seat holders accessing content | Content Controller data from LOMA | Top 50% of subscribing companies
Course completions by Learner | Content Controller data from LOMA | Top 50% of subscribing companies
Overall Experience with Industry Advantage
IA Liaison | LOMA survey | at least 80% positive
LMS Admin | LOMA survey | at least 80% positive
Learner | LOMA survey | at least 80% positive
Effect on employee retention* | Internal observation/HR data | net positive
Effect on job proficiency* | Internal observation | net positive
Note -- According to industry data, approx. 20% new employees resign in 1st 45 days; 33% with 6 months; 18.6% attrition annually in Fin Services.

## LOMA KPIs
KPI / IA Goal | Measurement tool | Suggested Goal | Result | Observations
Onboarding and Support
Time to allocate 50% of seats | Internal observation | 20 days
Time to allocate 100% of seats | Internal observation | 45 days
Quality/efficacy of LOMA-supplied promotional toolkit | LOMA survey | at least 80% positive
Ease of implementation | LOMA survey | at least 80% positive
Ease of overall IA administration | LOMA survey | at least 80% positive
Effectiveness of LOMA roll-out plan | LOMA survey | at least 80% positive
Effectiveness of LOMA inbound support | LOMA survey | at least 80% positive
Amount of technical issues | Internal observation | >80% of companies report technical issues within their acceptable tolerance
Content
Overall quality | LOMA survey | at least 80% positive
Positive impact on career development | LOMA survey | at least 80% positive
Format | LOMA survey | at least 80% positive
Length | LOMA survey | at least 80% positive
Breadth of topics | LOMA survey | at least 80% positive
Learning paths | LOMA survey | at least 80% positive
Alignment of content with business acumen curriculum | Internal observation
Course Star ratings | LOMA data | Average at least 4/5 overall
Usage
Percentage of seat holders accessing content | Internal LMS reporting | >80%
Course completions by Learner @ 60 days | Content Controller data from LOMA | 2+
Percentage of IA courses accessed @ 60 days | Content Controller data from LOMA | >40%
Benchmarking
Percentage of seat holders accessing content | Content Controller data from LOMA | Top 50% of subscribing companies
Course completions by Learner | Content Controller data from LOMA | Top 50% of subscribing companies
Overall Experience with Industry Advantage
IA Liaison | LOMA survey | at least 80% positive
LMS Admin | LOMA survey | at least 80% positive
Learner | LOMA survey | at least 80% positive
Effect on employee retention* | Internal observation/HR data | net positive
Effect on job proficiency* | Internal observation | net positive